## README
Lab 3 - Planning Backlog (spreadsheet tool)
Zainab ¦ SP24-BSE-034 ¦ Campus Event Management System
Blue text = cells you should edit with your own session data. Black = fixed content or formulas.
Sheets: WBS (Task 1), Backlog + Defences (Task 2), Local_Gap (Task 3), Prompt_Ledger (Task 4).
Sample rows are filled in as examples. Replace them with your real model outputs before submitting.
Versioning: this plan is tracked in the Git repo (see lab3 folder), as the lab requires.

## WBS
Task 1 - Reconciled Work-Breakdown Structure
Module | Task | Brief phrase / tag | ADDED reason
1 Auth & Accounts | 1.1 Account creation and login | ADDED | Brief never mentions accounts, but students and admins must be told apart
| 1.2 Role-based access (student/admin) | "admins add and remove events"
| 1.3 Session-token handling | ADDED | Omitted by the model; needed by every logged-in feature
2 Event Catalogue | 2.1 Event data model (title, date, venue, capacity) | "browse events"
| 2.2 Event listing / browse page | "students browse events"
| 2.3 Search and filter | ADDED | Browsing becomes unusable as the list grows
3 Registration | 3.1 Register for an event | "register"
| 3.2 Seat-capacity check | ADDED | Prevents over-booking
| 3.3 Cancel a registration | ADDED | Omitted by the model; counts drift without it
| 3.4 View my registrations | ADDED | Students need to see their sign-ups
4 Reminders | 4.1 Reminder scheduling | "get reminders"
| 4.2 Reminder delivery | "get reminders"
5 Admin Console | 5.1 Add an event | "admins add ... events"
| 5.2 Remove an event | "admins ... remove events"
| 5.3 Notify registered students on removal | ADDED | Removal after registration leaves students uninformed
Rows tagged ADDED: |  | 7
Invented task (quoted as the model produced it):
"Payment Gateway Integration: integrate Stripe/JazzCash so students can purchase tickets for paid events."
Why invented: the brief says nothing about payments, prices or tickets. The model over-read "register for events" as "buy a ticket".
Omitted by the model: session-token handling; cancel registration; Reminders as its own module.

## Backlog
Task 2 - Prioritised Backlog (MoSCoW)
ID | User story | MoSCoW | Justification
US-01 | As a student, I want to log in so that I can use personalised features. | Must | Nothing works without identity
US-02 | As a student, I want to browse upcoming events so that I can find ones I like. | Must | Core purpose
US-03 | As a student, I want to register for an event so that I secure a place. | Must | Core purpose
US-04 | As a student, I want to cancel my registration so that my spot frees up for someone else. | Must | Counts drift otherwise
US-05 | As a student, I want a reminder before an event so that I do not forget. | Must | Explicit in the brief
US-06 | As an admin, I want to add an event so that students can register for it. | Must | Without events the system is empty
US-07 | As an admin, I want to remove an event so that cancelled events disappear. | Must | Explicit in the brief
US-08 | As a student, I want to view my registrations so that I can see my schedule. | Should | Confirmation message covers launch
US-09 | As a student, I want a waitlist for full events so that I get a seat if someone cancels. | Should | Improves fairness, not essential
US-10 | As a student, I want to choose my reminder channel so that I get alerts where I prefer. | Could | Default channel is enough
US-11 | As an admin, I want to edit an event so that I can fix mistakes. | Should | Workaround: remove and re-add
US-12 | As a student, I want to be told when an event I registered for is cancelled so that I do not travel for nothing. | Should | Closes the cancellation gap
US-13 | As an admin, I want to export attendance to CSV so that I can report numbers. | Could | Not needed for launch
US-14 | As a student, I want to pay for tickets online so that I can join paid events. | Won't | Not in the brief; the model's invented task
US-15 | As an admin, I want slots blocked during Friday prayer and adjusted for Ramadan timings so that events never clash with campus hours. | Should | Local campus rule (see Local_Gap)
Summary
Must | 7
Should | 5
Could | 2
Won't | 1
Total | 15
Must % | 46.67% | Everything-Must backlogs score at most half, so keep this well below 100%.

## Defences
Task 2 - Three defended Must labels
Must story | Competing Should/Could story | Why the Must is Must and the other is not
US-04 | US-09 (Should) | Without cancelling, the seat count can never go back up, so data goes wrong the first time anyone changes their mind. A waitlist only improves fairness on full events.
US-05 | US-10 (Could) | Reminders are named in the brief, so one default reminder must ship. Choosing the channel is an enhancement on a working reminder.
US-06 | US-11 (Should) | With no way to add events there is nothing to browse or register for. Editing can be worked around by removing and re-adding.

## Local_Gap
Task 3 - A gap the model cannot see
Item | Content
Requirement | "Events must not be scheduled during the Friday congregational prayer window, and allowed event hours must change during Ramadan to follow the campus timetable."
Why no model could produce it | The exact prayer window and Ramadan timetable are local facts about my campus that appear nowhere in the brief.
Backlog row | US-15, Should
Note | Replace with a requirement that is genuinely true for your campus.

## Prompt_Ledger
Task 4 - Honest prompt ledger
Replace with your real prompts. Keep at least two failed or superseded attempts.
# | Prompt | Result | What I changed and why
1 | Plan a campus event system. | Failed: vague, generic essay | Added role, output shape, module count
2 | Act as a software project planner. Break the Campus Event Management System into 4-6 modules. For each module list 3-5 concrete engineering tasks. Give the result as a nested list. | Superseded: invented a payment task, skipped session tokens and cancel | Reconciled by hand; banned inventing tasks
3 | Same as before, but only include tasks supported by this brief: [brief]. Mark additions as ADDED. | Better: no payment task, additions labelled | Moved on to stories
4 | Rewrite these tasks as user stories in the format 'As a <role>, I want <goal> so that <benefit>.' Then apply MoSCoW prioritisation with a one-line justification per label. | Worked but labelled almost everything Must | Asked for justifications and argued by hand
5 | What did you miss? List risks and gaps in this backlog. | Found the cancelled-after-registration gap | Added US-12
Attempts logged: | 5